AR, Time, Tunnel Length and Geology Using QTBM

Nick Barton

NB&A, Oslo, Norway

# Introduction

In this chapter we will focus more on advance rate (AR) than penetration rate (PR), and focus on the effect of tunnel length and geological variations, and therefore the fundamental question of time (T). Case records from 1,000km of mostly open-gripper TBM will be supplemented with a synthesis of world records for different sized TBM and their variation with time. Two fundamental questions will finally be addressed: is it correct to use TBM ‘because the tunnel is so long’? And is it correct to use TBM: ‘because conditions will be bad’? Logic suggests that in general the rock mass quality statistic, for instance described by the Q-value, will contain more outliers such as more serious fault zones, or more cases of exceptionally hard massive rock, the longer the planned tunnel. It is the outliers that will have the strongest influence on AR and therefore total project time. The QTBM prognosis method will be described and illustrated with examples, including Follobanen where four Herrenknecht double-shield TBM drove approximately 9km each. The use of seismic refraction results and correlation of P wave velocity (VP) with Q and therefore QTBM prognosis will be demonstrated.

The following symbols will be used: PR (m/hr), means the penetration rate with continuous boring, while AR is the actual advance rate e.g. in m/week, m/month, m/year. U is utilization which depends on machine-type, diameter, geological conditions and on the time period considered, while time T is total time: such as 24hrs, 168hrs, 730hrs, 8730 hrs, for a day, week, month and year. If each AR time period is given in m/hr then the influence of time and tunnel length can be better understood. U is very much a time-dependent variable, and 24 hours tells little.

The two blue cubes in Figure 4.1 correspond almost exactly to the overall mean values of PR, AR, and UCS (200MPa) for the four double-shield TBM driving approximately 9km each at the Follobanen rail tunnels south of Oslo. They also apply very closely to four TBM at the Guadarrama rail tunnels which each tunneled 14km, though here the UCS was more variable and the overall AR was 0.55m/hr. The above data in Figure 4.1 means shows that AR (in m/week) has a more rapid decline in these long tunnels.

Fig. 4.1 These two trend curves for PR and AR are from tabulated data given by Fawcett (1993). The resulting figure was published in Barton (2000). The data points refer to average PR and AR (m/week) in shale, tillite and hard sandstone with respective UCS = 50, 150 and 250MPa. They are symptomatic of TBM behavior trends. More delays in AR in weaker rock because stability may be an issue, and possibly severe cutter change delays in AR in very hard rock

In Figure 4.2a we see PR trends for 2.8km of TBM tunnelling in variably jointed granites (UCS from 130 to 250MPa), correlated with Q-values. Logging was performed on a continuous basis in the open-gripper TBM back-up area.

It should be noted that Figure 4.2b has, at present, inappropriate adjectives for TBM. When the QTBM equation is presented later, they will be made appropriate. For example, when Q>100, ‘tough boring’ will be seen, not ‘extremely good’. One further temporary ‘error’ is shown: there should be multiple AR curves for e.g. 1 week, 1 month, 3 months, 1 year etc. These will be shown later in relation to QTBM.

# Trends from thousands of kilometers of TBM

In Figure 4.3 a and b we see a synthesis and then the raw data from the Barton (2000) analysis of some 1000km of data from 145 well-documented lengths of mostly open-gripper case records. PR (m/hr) applies only to the left axis in each of the figures. The remaining area of the diagrams and all the data apply to AR and time T, each on a log-scale. The deceleration gradients (-m) range from about -0.15 to -0.25 when Q-values are above 1.0, but as seen by the dotted curves they decelerate more rapidly (more negative gradient m) as Q-values decline to 0.1, 0.01 etc. Crosses: real TBM.

Perhaps of surprise is that even world record TBM performances (mostly from Robbins) when gathered in common size ranges (Barton 2013) show the same trends of deceleration, which mostly match the open-gripper case record trends. An obvious scale effect is also seen in Figure 4.4 and clearly needs to be incorporated in PR and AR prognoses, as suggested in Macias and Barton (2022).

Fig. 4.2. a) Comparison of penetration per revolution with the regular Q-value in granites, except that Jr and Ja were averaged for all joint sets. (Sundaram and Rafek 1998). b) PR and AR trends graphed on a regular Q-value ‘tunnel stability’ chart (Barton 2000).

# The QTBM prognosis method

When developing the QTBM method in 1999-2000 (Figure 4.6) it appeared that rock mass quality was sufficiently described with the Q-system. There were however two important additional factors to be addressed. Firstly, the RQD term needed to be specifically estimated in the tunnelling direction, so an oriented RQD0 was required. Also, although it was obvious that UCS was an important parameter, the action of UCS within a jointed rock mass would be less direct so a rough estimate: SIGMA was suggested, based on Qc = Q × UCS/100. The equation for SIGMA gives a ‘rock mass strength’ estimate ranging from about 1MPa to 100MPa depending also on how massive the rock is. This may be realistic. However, nobody knows UCS ROCK MASS.

| QTBM=RQDoJn∙ JrJa∙JwSRF∙SIGMAF10209∙20CLI∙q20∙σθ5 | (4.1) |
| --- | --- |
| SIGMA≈5∙γ∙Qc 1/3 | (4.2) |

Fig. 4.3 Open gripper data from Barton (2000). a) synthesis of trends with suggested nomenclature WR (best), good, fair, poor. b) Raw data: best, average, worst. The black crosses (+ far right) are permanently buried TBM

The equation for QTBM shows that SIGMA is compared with a typical cutter force (F) normalized by 20 tons. There is strong evidence in the literature that comparing ‘stress and strength’ is a sound geotechnical operation, as TBM sometimes show reduced PR despite operators increasing cutter force because of high strength and massive rock. Moving further along the equation, CLI is the cutter life index, a well-documented parameter from NTNU/SINTEF, Trondheim. It is normalized by a typical value of 20. Low values, as for instance 5 for quartzite give higher QTBM and slower progress. Quartz content (q) in % is normalized by a neutral value of 20%. Finally, a confining pressure term σθ is normalized by an estimated 5MPa biaxial stress state on the tunnel face, per 100m depth, based on a 2D tangential stress concentration factor (Kirsh theory) and assuming a rock mass density of 2.5gr/cm3.

Fig. 4.4 In addition to the world record data for three diameter ranges (see cubes, derived from Figure 4.5) a solid black and nearly parallel thin blue line are shown. These stretch from mean PR ≈ 2.0 m/hr out to final AR of 0.5 and 0.55m/hr and apply to the 4x9km Follobanen TBM and the 4x14km Guadarrama TBM rail tunnels in Norway and Spain. Each of these were driven most of the time in double-shield mode and show shallower deceleration gradients, at best approximately half those of open-gripper TBM. The world records suggest a strong scale effect, with smaller diameter TBM clearly the fastest.

Short-term (24hr) AR as high as 5m/hr appear possible judging by world records (Figure 4.4). However, values of AR as high as 3m/hr beyond 1 month duration appear to be impossible (World record for 1 month, ≈ 720 hours = 2,163m).

The author of this chapter has applied the QTBM method to TBM projects in several countries (Brazil, Chile, Peru, South Africa, Hong Kong, Australia, Spain, Norway). The demonstration of QTBM shown in Figure 4.7 is a suitable introduction. Figure 4.8 illustrates the use of QTBM for a mine tunnel in Chile.

# Lessons learned via QTBM at Follobanen 4 × 9km

The Follobanen TBM tunnels, which were driven from a central assembly hall, saw two 9.9m diameter Herrenknecht double-shield TBM boring to the north towards Oslo, and two boring south towards Ski. The tunnels were mostly driven during 2016 and 2017. In 2009, some two years into the BaneNor investigations for the future tunnels, the author of this chapter was invited to perform Q-logging of relevant exposures mostly along road-and-motorway cuttings, at major building sites and in quarries, both in the neighborhood of the planned northern tunnels, and as near as possible to the more laterally distant southern tunnels (Figures 4.9 and 4.10). The planned tunnels would be mostly 70 to 100m deep, but with a range of 30 to 160m.

Fig. 4.5 Robbins web-site data: TBM world records. Mostly Robbins, occasional Wirth, and Herrenknecht. Bottom-right: some details of problems at the Channel Tunnel (UK-France) outside the majority of the less-jointed chalk marl where world records were broken.

Fig. 4.6 The QTBM method of estimating PR and a time-dependent AR, here drawn for 1 day, 1 week and 1 month. Higher short-term AR can be obtained with higher PR, but conveyor belt capacity may be compromised beyond the 6 to 8m/hr range of PR.

Fig. 4.7 Left axis: demonstration of PR prognosis (with F = 28 or 26 tnf) PR, and the differentiation of single-shield (cube) and double-shield (star) deceleration trends. At best double-shield may show ½ x (-)m compared to open gripper TBM. An untreated major fault: the lowest line ‘stops the TBM’ (Calculated 3494 months in simulation ≈ 300years)

Clearly, surface exposure logging will not pick up reliable data for typical 70 to 100m tunnel depths. A partial improvement could be the use of seismic refraction data and drill core. Unfortunately, both (as available in 2009) were focused on weakness zones. These were assumed by the owner to be the source of potential delay. In fact, with the benefit of subsequent hind-sight, it was the more dominant rather massive, high VP and high UCS, ‘hard mixed-face’ nature of the rock mass that was the source of many cutter ring and bearing problems (Macias and Barton, 2022). Water inflow problems and delaying pre-injection due to unusually high horizontal permeability were also a factor in the southern tunnels. Such problems were not yet identified at the time of e.g. Barton and Gammelsæter (2010) prognoses.

A QTBM input option for shallow tunnels, is to directly apply the P-wave velocity in place of the Q-parameters. Recorded VP velocities are automatically converted to Q-values, using the following empirical relations:

| VP(km/s)≈logQC+3.5 | (4.3) |
| --- | --- |
| QC=Q UCS(MPa)100 | (4.4) |

The inverse is:

| Q≈100UCS ∙ 10(VP-3.5) | (4.5) |
| --- | --- |

when VP = 3.5 km/s, and UCS ≈ 100 MPa, Q ≈ 1. As will be seen in Figure 4.11, links between QC and VP are available also with approximate correction for depth (Barton 1995, 2007).

Fig. 4.8 Application of QTBM for a mine axis tunnel in Chile. In this unusual case there were several very deep drill-core available, drilled mainly to analyse the orebody. An early faulted zone with adverse Jn/Jr of 15/1.5 and Ja = 2 (weathered) caused a 1month delay due to excessive overbreak so ‘over-boring’ in terms of volume of cuttings and blocks (Imagine as lowest blue line). The prognosis of some 60 weeks (longest red line, final AR = 0.8m/hr) for 5km proved over-optimistic due to severe labour laws with workers being transported several kilometers to a miner’s hostel each lunch ‘hour’! If the reader expands the scale, the left-hand input data screen shows four narrow faults. These give the steepest deceleration. The last ‘zone 11’ of 100m length has the assumed Q-parameters shown.

Weakness zones which had been identified by low velocities in seismic refraction profiles along the planned rail tunnel corridor (as of 2009) were modelled with QTBM. An example of an input data screen is shown in Figure 4.12. The appearance of one of these weakness zones is shown in Figure 4.13. Blue pencils mark the soft clay core.

Preliminary seismic data provided by the Owner in 2009 is reproduced in Table 4.1. There was then no further update from the Owner. The author returned to the project in 2018, now assisting the contractor in a major claim. Seismic evidence of major lengths of high velocities was now seen (Table 4.2). This has a significant impact on more relevant prognosis if it had been made available in a timely manner.

Updated prognoses could now be made which were confirmed by the results of tunnelling the 4 × 9km (Table 4.3 and 4.4). Figure 4.14 is one example. There was now a focus on longer sections of high velocity, high Q, and higher Qc due to the challenging hard rock UCS.

Fig. 4.9 Four of more than 300 examples of surface exposures/cuttings/quarries with locations generally within 1km of the future Follobanen rail tunnels. Hard, pre-Cambrian tonalitic gneisses, granites, pegmatites and amphibolites, with UCS from 150 to 300MPa.

Table 4.1   Preliminary seismic refraction measurements focused on low Q-value-and-low-velocity weakness zones where potential delays were assumed. Data available in 2009.

| Approx Q-value in 25m depth | 0.01-0.03 | 0.03-0.1 | 0.1-0.3 | 0.3-1.0 | 1.0-3.2 | 3.2-10 | 10-32 | 32-100 | 100-320 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vp (km/s) | 1.5-2.0 | 2.0-2.5 | 2.5-3.0 | 3.0-3.5 | 3.5-4.0 | 4.0-4.5 | 4.5-5.0 | 5.0-5.5 | 5.5-6.0 |
| No. of measurements in range | I (1) | III (3) | IIIII IIII (9) | IIIII (5) | IIIII IIIII IIII (14) | IIIII IIIII IIIII II (17) | IIIII IIIII IIII (14) | IIIII IIIII IIIII IIIII IIIII (25) | IIIII (5) |
| Thickness of weakness zones ≈ (m) | 15 22 | 13 20 31 30 8 | 8 35 6 10 11 9 17 40 | 16 40 15 8 | 8 15 |  |  |  |  |
| Sum of thicknesses ≈ (m) | 37 | 102 | 136 | 79 | 23 | Ʃ=377 m recorded with various seismic profile directions, typically NNE and WSW in ‘focused’ lows |  |  |  |

Fig. 4.10 Q-histogram logging of more than 300 rock-cuttings and rock exposures in the general area of the North and South tunnels, but often as much as 1 km distance in the case of the southern tunnels due to a lack of rock exposures caused by a diverging motorway

Fig. 4.10 Continued

Fig. 4.11 Empirical links between P-wave velocity and Q or Qc with approximate correction for depth or stress level (Barton 1995, 2007). Blue rectangle: VP = 5.5km/s, depth 25 -100m, Qc = 40 to 100, Q = 20 to 50 if UCS = 200MPa

Fig. 4.12 Direct use of shallow refraction VP velocities in place of Q parameters. Zone 9 input data assumptions for machine-rock interaction are shown along the bottom keys

Table 4.2 A more complete description of the rock mass to be tunneled through with seismic refraction measurements also along sections of the future tunnels with high velocities and high Q-values (Made available to the author in 2018, since now working for the contractor). Note the dominance of VP = 5.0 to 5.5 km/s, and many assumed Q-values of approx. 30 to 100. This helps to explain the greater difficulties with the four Herrenknecht TBM, since many more kilometers of hard, high-VP, high-Q, high-Qc and in particular high QTBM rock masses.

| Approx Q-value in 25m depth | 0.01-0.03 | 0.03-0.1 | 0.1-0.3 | 0.3-1.0 | 1.0-3.2 | 3.2-10 | 10-32 | 32-100 | 100-320 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| VP (km/s) | 1.5-2.0 | 2.0-2.5 | 2.5-3.0 | 3.0-3.5 | 3.5-4.0 | 4.0-4.5 | 4.5-5.0 | 5.0-5.5 | 5.5-6.0 |
| Number of measurements in given VP range | II | III II I II I II | IIIII II I III IIII IIII | I II II IIIII IIIII IIII | I I I IIII IIIII | IIIII IIII III III I I | IIIII II IIIII IIII IIIII IIIII IIIII IIIII I IIIII IIII | IIIII IIIII IIIII IIIII II IIIII IIIII II IIIII II IIIII IIIII II | IIII IIIII I IIIII |
| Total number | 2 | 11 | 19 | 19 | 12 | 17 | 49 | 53 | 15 |
|  |  |  |  |  |  | Well jointed | Sparse jointed | Quite jointed | Massive rock |
| Sum of thicknesses ≈ (m) | 138 | 221 | 252 | 242 | 311 | 975 | 2769 | 3229 | 771 |

Table 4.3 The overall results for the four Follobanen Herrenknecht TBM are tabulated here. Records show that all the four TBM were struggling to reach up to 0.4 to 0.6m/hr AR and the final mean result after approximately 2 years was 0.49m/hr (Macias and Barton 2022)

| TBM | m | Start date | Finish date | Weeks/hrs (appr) | PR (mean) m/hr | AR (mean) m/hr |
| --- | --- | --- | --- | --- | --- | --- |
| TBM 1 N | 8.898 | 5 Sept 2016 | 5 Sept 2018 | 105/17640 | 1.9 | 0.50 |
| TBM 2 N | 8.908 | 6 Oct 2016 | 5 Sept 2018 | 101/16970 | 1.9 | 0.52 |
| TBM 3 S | 9.142 | 30 Nov 2016 | 26 Feb 2019 | 116/19490 | 2.0 | 0.47 |
| TBM 4 S | 9.129 | 7 Nov 2016 | 26 Feb 2019 | 119/19990 | 1.9 | 0.46 |

Table 4.4 Some of the input data and calculations for the 6 zones modelled, showing Q values ranging from 37.5 to 150, and Qc values ranging from 70 to 315. The range of calculated QTBM values, with input for zone 6 shown in Figure 4.14a, is 18 to 345 (see bold). Calculated PR for the six modelled zones ranges from 1.55m/hr to 2.81m/hr, and AR from 0.51m/hr (the dominant 6km) up to 1.61m/hr (for a modelled 250m long zone)

| Zone | Lithology |  | Stability |  | Oriented |  | Rock mass strength |  |  |  |  |  |  |  |  | QTBM |  | Gradient |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q |  | Q0 |  | Qc |  | QT |  | SIGMACM | SIGMATM |  | SIGMA |  |  |  | m |
| 1 | Tonalitic gneiss |  | 150.00 |  | 150.00 |  | 315.00 |  | 0.00 |  | 95.29 | 0.00 |  | 95.29 |  | 345.49 |  | -0.17 |
| 2 | Granitic gneiss |  | 71.25 |  | 71.25 |  | 171.00 |  | 0.00 |  | 77.71 | 0.00 |  | 77.71 |  | 130.04 |  | -0.18 |
| 3 | Biotite gneiss |  | 45.00 |  | 45.00 |  | 69.75 |  | 0.00 |  | 59.69 | 0.00 |  | 59.69 |  | 67.36 |  | -0.15 |
| 4 | Amphibolite |  | 37.50 |  | 37.50 |  | 103.13 |  | 0.00 |  | 70.34 | 0.00 |  | 70.34 |  | 17.75 |  | -0.11 |
| 5 | Granitic gneiss |  | 45.00 |  | 45.00 |  | 108.00 |  | 0.00 |  | 66.67 | 0.00 |  | 66.67 |  | 64.43 |  | -0.15 |
| 6 | Tonalitic gneiss |  | 47.50 |  | 47.50 |  | 97.38 |  | 0.00 |  | 64.41 | 0.00 |  | 64.41 |  | 65.70 |  | -0.15 |
| 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.00 |  | 0.00 |
| 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.00 |  | 0.00 |
| 9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.00 |  | 0.00 |
| 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.00 |  | 0.00 |
| Zone |  | Lithology |  | Penetration |  |  |  | Time to advance |  |  |  |  | Overall performance |  |  |  |  |  |
|  |  |  |  | PR |  | AR |  | T |  | check |  |  | SL |  | ST |  |  |  |
| 1 |  | Tonalitic gneiss |  | 1.55 |  | 0.54 |  | 458.85 |  | 250.00 |  |  | 9000.00 m 9.00 km |  | 16382.39 h 22.75 months |  | PRL (av) |  |
| 2 |  | Granitic gneiss |  | 1.89 |  | 0.67 |  | 373.19 |  | 250.00 |  |  |  |  |  |  | 21609.00 |  |
| 3 |  | Biotite gneiss |  | 2.22 |  | 0.94 |  | 264.89 |  | 250.00 |  |  |  |  |  |  |  |  |
| 4 |  | Amphibolite |  | 2.81 |  | 1.61 |  | 155.23 |  | 250.00 |  |  |  |  |  |  |  |  |
| 5 |  | Granitic gneiss |  | 2.17 |  | 0.75 |  | 1326.33 |  | 1000.00 |  |  |  |  |  |  |  |  |
| 6 |  | Tonalitic gneiss |  | 2.16 |  | 0.51 |  | 13803.89 |  | 7000.00 |  |  |  |  |  |  | ART (av) |  |
| 7 |  |  |  | 0.00 |  | 0.00 |  | 0.00 |  | 0.00 |  |  |  |  |  |  | 0.5494 |  |
| 8 |  |  |  | 0.00 |  | 0.00 |  | 0.00 |  | 0.00 |  |  |  |  |  |  |  |  |
| 9 |  |  |  | 0.00 |  | 0.00 |  | 0.00 |  | 0.00 |  |  |  |  |  |  |  |  |
| 10 |  |  |  | 0.00 |  | 0.00 |  | 0.00 |  | 0.00 |  |  |  |  |  |  |  |  |

Fig. 4.13 The photo is one of the weakness zones that was Q-logged. The Q-histogram statistics for seven such zones are shown. The QTBM model shows a predicted 3 months delay (due to steep -m gradients). Input data was based on VP data from focused refraction seismic above nine simulated weakness zones. In these simulations, no pre-treatment has been modelled, meaning the delay caused by pre-injection (doubled –m, approx.)

Fig. 4.14 The six modelled lengths demonstrate mean PR = 2.3m/hr (slightly high). The final AR = 0.5m/hr, is identical to that experienced on average in the 36km of Follo Line TBM tunnelling, with four Herrenknecht TBM. Note that the ‘zone 6’ dominant 7km, as shown on the input data screen, has an assumed Q = 95/3 × 1.5/1 × 1/1 = 47. In fact, the most frequent Jn observation in TBM face logging was 2.0 (one set), and Jn = 4 (two sets).

# Fault zones and their challenge to TBM

Fault zones are of course a challenge to all methods of tunnelling. For some years TBM manufacturers have been advertising that TBM, in particular double-shield, are faster than drill-and-blast, both for bad rock and for long tunnels. In connection with such claims the gradually improved ability to perform pre-injection which has been noted during several decades, clearly brings TBM closer to tackling the worst of fault zones. Three examples of challenging fault and fractured zones follow here, with an assessment of how they impacted the TBM tunnelling. See Figures 4.15 to 4.20.

The TBM manufacturers claim are tested frequently in some tunnels, and sometimes TBM have to be replaced by drill-and-blast when the complexities of some faults even overcome the machines’ and the operators’ and the designers’ ingenuity. On other occasions pre-injection, if it is planned and therefore possible, can save the project. There are many examples of this.

Fig. 4.15 Mine access tunnel in Chile driven with double-shield SELI machine. In an unexpected first one month, the TBM operators struggled with ‘over-excavation’ in a fractured zone with ‘too many’ joint orientations. When Jn/Jr ≥ 6, over-break or over-boring is likely, and in this particular zone Q ≈ 40/15 × 1.5/4 × 1.0/2.5 = 0.4 ‘very poor’ (i.e. Jn/Jr ≥ 6) (see Figure 4.16 for ‘overbreak’ rule from Q)

Fig. 4.16 In drill-and-blast tunnels the rule-of-thumb for almost inevitable overbreak is when the Q-system based ratio Jn/Jr ≥ 6. This will tend to affect TBM also, especially if assisted with adverse Ja (weathering, clay coatings, clay fillings). These important factors Jn, Jr and Ja are not adequately represented when just adding joint sets as in the NTNU prognosis method. It is hard to compare the NTNU and QTBM methods of prognosis because the former is missing the reasons for over-break. This is not just the sum of joint frequency or spacing.

The contractor’s solution for void formation was filling with foamed resin, an after-the-event measure that is actually too late, as a few meters per day was the limits of advance and the zone of over-excavation continued for several weeks in Chile. Note that a tunnel fire can be caused if too large volumes of chemical grout mix are needed for void filling. ‘Waiting for the smoke’ (to clear), was unexpectedly different from ‘waiting for the train’ on a pie-diagram. The problem with this TBM was that ring-mounting equipment had to be dismantled before pre-injection drilling could be performed, clearly not the ideal choice of priority if faulted rock is expected. How to do both (build rings and pre-inject) when both were needed was not solved.

Fig. 4.17 Over-boring due to over-breaking fractured rock without significant clay is a problem that was encountered in the Chile mine access TBM, Figure 4.15. Filling the frequent voids in the arch and between fallen blocks is not solving the reason for, or preventing, the over-boring. Pre-injection with cement grouts could have been

A particularly challenging series of fault ‘swarms’ was experienced at the Pont Ventoux hydroelectric project in Northern Italy (see Figures 4.18 and 4.19). These were not expected but were gradually encountered at the down-stream end of the tunnel as the TBM gradually curved towards the upstream and became sub-parallel to the swarm of faults.

Fault zone delays on TBM can be convincingly explained by a ‘theo-empirical’ equation, as shown in the fault zone example from the ultra-challenging Pinglin tunnels in NE Taiwan (Shen et al., 1999). A particularly challenging situation is illustrated in Figure 4.20. The writer was able to visit Pinglin project during several by-pass situations. Eventually all three TBM were replaced by drill-and-blast. One was destroyed in a fault zone.

The simple equations shown in Figure 4.20 need to be understood. The first three are obvious assuming that U is acknowledged to be time-period dependent (Figures 4.3 and 4.4 show overwhelming support for this). The fourth equation explains why serious fault zones (with low Q and steep deceleration due to negative -m) are such a serious threat, unless the effective Q-value can be improved by successful pre-injection. Without this improvement the ‘too large’ component 1/(1+m) in equation 4 (Figure 4.20) may be too large, to the extent that a TBM may need to be left in the mountain and a drill-and-blast bypass constructed for D+B completion. A comparison of TBM and D+B is shown in Figures 4.21 and 4.22. The mean Follobanen experience is drawn in Figure 4.22.

Fig. 4.18 An example of problems encountered with one of the faults at chainage 2498-2517m, Pont Ventoux, Italy. The following is a summary. 1. Clay compromises grippers. 2. Plentiful water erodes a shaft and loosens blocks. 3.Tunnel stability reduces.4. Cutter-head is repeatedly blocked. See Figure 4.19 for specific details experienced during 5 months

Fig. 4.19 This sub-parallel fault was encountered for some 30m and delayed the project by 5 months. A ‘natural’ shaft developed above the cutterhead. It was eroded by water and falling blocks. The final result was a bypassed TBM (see one of the distant crosses in Figure 4.3a). (Figures, photos from Karl Gunnar Holter and NB. The author superimposed the dated over-break records of KGH)

Fig. 4.20 Top-left is the suggested link between the regular Q-value and the deceleration (-)m. This was published in Barton (2000). With the benefit of projects such as Follobanen, Guadarrama and Gastau (Brazil) driven in particularly high-Q, high-UCS rocks a ‘U-shaped’ trend curve could now be envisaged, climbing as sketched when QC-values are ‘too high’

# Why long TBM tunnels may not be faster than D+B – hybrid suggestion

Each and every tunnel, whether drill-and-blast or TBM will have a geologically determining rock mass quality statistics. In Figure 4.23, it is modelled on hypothetical Q-system rock classes. A shorter, shallower tunnel is shown and a deeper, longer tunnel. The former may have boreholes and refraction seismic, the latter usually has a lot of relatively unknown hydro-geological details, even if the expected geology seems to be well understood. For the above reasons the two tunnels are given slightly different Q-class predictions. Note the ‘tails’ (low Q, high Q) that are different.

Fig. 4.21 Comparison of a moderate TBM project (5km in 1 year) showing dependency on ideally jointed conditions if to remain faster than drill-and-blast (Barton 2000 with additions). The boxes emphasize the two delaying factors for TBM where drill-and-blast may be faster. Note the world record SVEA data for 5.8km of D+B in coal-measure rocks on Svalbard

Fig. 4.22 The added ‘rectangle’ assumes a Q-value of ≈ 40, intersecting an approx. 2 years predicted result and with mean ≈ 80m/week on the vertical axis. Mean completion time for the four 9km tunnels: 110 weeks from Table 4.3 (Check: 0.49m/hr = 168 × 0.49 = 82m per week average, 82 ×110 ≈ 9.02km. Mean tunnel length = 9.02km)

Although only hypothetical, it is quite likely that the major (FF) faults shown in Figure 4.23 have allowed valleys to be carved out by glacio-fluvial processes. If so, then multiple ‘attack points’ (and ventilation) could be available for an early start by drill-and-blast, while waiting for TBM delivery. Reserve the better investigated and perhaps lower-cover sections for the subsequently delivered TBM. They will be tunneled much faster once they start boring. This deliberate hybrid approach was recommended previously in a Chinese Academy of Engineering workshop (Barton 2012).

With their huge high-speed rail network and record number of TBM tunnels, the experience within China is exceptional. Nevertheless, to give ‘geology’ the influence it deserves, it is a fact that a Millenium Tunnel project in China required acceleration by drill-and-blast to achieve completion within the deadline. This was a case of an unplanned hybrid solution.

Fig. 4.23 Left: lower cover, better investigated tunnel where TBM will likely out-perform drill-and-blast by a considerable margin (except for the delivery/assembly time delay). Right: a much longer, deeper tunnel with the likelihood of a number of major faults (FF) and harder more massive rock (HH). The ‘extremes’ at either end of the QTBM scale (Figure 4.6) may delay the one (or two) TBM more than expected

# The ultimate challenge of TBM tunnels that are too deep

The author has had the opportunity to review and suggest solutions for some of the deepest TBM tunnels, meaning 2km or more, including the Olmos Tunnel through the Andes in Northern Peru, and the massive Jinping II headrace tunnels in China with four parallel tunnels: two TBM and two drill-and-blast, and the tragically ending pilot TBM of smaller diameter, in which there were many fatalities due to a massive rock burst. This had reached the high overburden region first.

The problem is initially two-fold: too high cover (several kilometers at > 2km depth) and in the case of Jinping II insufficiently strong marble. A simple Kirsch-based elastic-medium calculation showed that the most simplistic 2 × 2,000 × 2.5 /100 MPa = 100MPa estimate of tangential stress, even higher with stress anisotropy, was too close to the approximately 90 to 120 MPa UCS of the marble.

The standard (but actually misinterpreted) rule-of-thumb is that ‘stress-induced’ fracturing begins when σθ maximum reaches 0.4 × UCS (+/- 0.1) from Martin et al. (1999) and shown in Figure 4.24. The observed onset of ‘stress’ induced fracturing at a similar stress/strength ratio of ‘0.4’ has been part of the Q-system SRF factor since earlier (Grimstad and Barton 1993).

Fig. 4.24 Due to their cylindrical/circular shape and ‘slow’ method of excavation, TBM tunnels maximize the likelihood of Kirsch-based elastic theory applying. The above example giving a 100MPa estimate for σθ max is the elementary first step ready for comparison with UCS or σc. Left: Hoek and Brown (1980). Right: Martin et al. (1999). Clearly when UCS for marble is 90 to 120MPa, and the tangential stress is at least as high as 100MPa, then major problems must be expected. The author recommended removal of the TBM at Jinping II, but this did not occur until after the major fatalities in the pilot bore, with final completion of all tunnels by drill-and-blast. Remarkably there are now ‘high-stress’ (rock-burst) research laboratories parallel to the completed tunnels, where cover exceeds 2km

This is shown in Table 4.5 by the rapidly ‘accelerating’ values of SRF as the ratio 0.4 was exceeded. In fact, the fracture initiation explanation is due to something else. The uniaxial compressive strength of rock is not its lower-bound strength, nor is cohesive strength, while tensile strength is, when combined with Poisson’s ratio. The explanation is shown in Figure 4.25, from Barton and Shen (2017).

Table 4.5   The empirically based ‘acceleration’ of SRF after the stress/strength ratio has exceeded ≈ 0.4 (Grimstad and Barton 1993). Higher SRF gives lower Q-value, hence heavier support, especially based on fibre-reinforced energy absorbing shotcrete, and bolts that can yield, such as grouted D-bolts

| b) Competent rock, rock stress problem |  | sc/s1 | sq/sc | SRF |
| --- | --- | --- | --- | --- |
| H | Low stress, near surface, open joints. | > 200 | < 0.01 | 2.5 |
| J | Medium stress, favorable stress condition. | 200-10 | 0.01-0.3 | 1 |
| K | High stress, very tight structure. Usually favorable to stability, may be unfavorable for wall stability. | 10-5 | 0.3-0.4 | 0.5-2 |
| L | Moderate slabbing after > 1 hour in massive rock. | 5-3 | 0.5-0.65 | 5-50 |
| M | Slabbing and rock burst after a few minutes in massive rock. | 3-2 | 0.65-1 | 50-200 |
| N | Heavy rock burst (strain-burst) and immediate dynamic deformations in massive rock. | < 2 | > 1 | 200-400 |

In carefully instrumented uniaxial compression tests, acoustic emission is also seen to start at the stress/strength ratio of ‘0.4’. The reasons are actually the arithmetically equal ratio of tensile strength and Poisson’s ratio: 0.4 × UCS ≈ σt /ν, (Figure 4.25). This more correct explanation of fracture initiation was discovered by Baotang Shen (Shen and Barton 2018). Shen was the developer of the fracture mechanics based FRACOD code which is seen applied to highly ‘stressed’ (or strained) TBM simulations in Figure 4.25 (Old Beaumont TBM) and in Figure 4.26 (1,000m deep simulations in granite) showing the ‘positive’ effect of jointing in dissipating the highest stress and strain.

Roughly speaking, strain-induced tensile fracturing will start in a TBM driven in massive rock when the estimated tangential stress reaches 4x to 5x σt, since Poisson’s ratio is often 0.2 to 0.25. If stresses are much higher, propagation in unstable shearing (rock burst) may occur (Shen and Barton 2018).

Fig. 4.25 The explanation for extension strain caused extension fracturing (red) with propagation in shear (green) from FRACOD modelling by Baotang Shen. The rule-of-thumb that fracturing (and AE in a laboratory test) start when the tangential or major stress reaches 0.4 × UCS (+/- 0.1) is more correctly given as tensile strength divided by Poisson’s ratio. The photograph is of the Old Beaumont TBM pilot tunnel from 1880, driven about 1km, 110 years before the nearby Channel Tunnel in the same chalk marl. Here the tunnel has curved under a 70m high cliff, which was enough to increase the tangential stress by several MPa, which was sufficient to fracture the weak 4 to 9MPa rock (Barton and Shen 2017)

# Conclusions

- A principal finding from case records, both open-gripper, double-shield and world record performances is that, after the learning curve there is deceleration of advance rate (AR) due to reduction of utilization (U) as challenges appear as the tunnel gets longer (factors such as difficult faults, excessive water, pre-injection needs, abrasive hard rock, soft-mixed-face, hard-mixed-face, increased cutter ring and bearing replacement). U needs to be recast as Tm where T is total hours (24, 168, 720, etc.) and m is the negative deceleration gradient.

Fig. 4.26 FRACOD modelling by Shen of hypothetical 1,000m deep TBM tunnel in massive unjointed, and partially jointed rock masses with the same strength properties, but with simple Mohr-Coulomb ‘c and ϕ’ jointing. Minor displacement on the joints dissipates to some extent the highest stresses. The damage caused by drill-and-blast as compared to the ‘non-damaging’ TBM is the reason for the occasional need to not rely on TBM when tunnels are exceptionally deep and the rock is not strong enough

- There is a need to estimate rock mass strength to compare with cutter force in TBM prognoses. Sometimes PR may reduce despite increased cutter force. The number of joint sets Jn and joint properties Jr and Ja in the Q-rating obviously affect over-break and local cutter action, and the potential for over-boring, so they are also needed and are important parts of QTBM.

- Descriptions of the rock mass are limited to each 24 hours (maintenance shift) in double-shield with PC-elements. So double-shield case records with logging at only 15, 25, or 35m, etc., intervals may be unreliable in relation to continuous open-gripper rock mass descriptions. Critics (of other’s TBM prognoses) should be careful using such sporadic ‘data’.

- Pre-injection helps to improve most of the six Q-parameters, so the deceleration gradient (-m) is made less negative. This means fewer long delays for the TBM, despite the time needed for the pre-injections.

- A simple formula that describes why there may be major delays in low Q-value fault zones has been available for more than two decades. Improvement of the effective ultra-poor quality of fault zones with flushing and cement injection ahead of the face using multiple boreholes can help here. The Q-value is effectively improved.

- Pre-injection will also be needed to control against groundwater drawdown and settlement damage. The problem is that TBM may get delayed before the water-tight lining reaches the leaking zone, so avoiding damage caused by groundwater drawdown is helped by pre-injection after discovery of permeable zones by multiple, continuous probe drilling.

- Do not ‘automatically’ choose TBM for long tunnels. A ‘hybrid’ solution might have advantages. Drill-and-blast the deeper and less investigated sections, if intermediate access is possible, while waiting for TBM delivery for fast excavation of the better investigated sections. Help maintain the good reputation of TBM. There have been many bad decisions and final forced hybrid with TBM destroyed or remaining in the mountain, and regrettable multiple fatalities in well-known cases such as in Taiwan, China, Pakistan. In the case of Taiwan it was just the severely faulted rock mass, not great depth.

- The assumption of ‘stress-induced’ fracturing when the estimated maximum tangential stress reaches approx. 0.4 × UCS in deep hard-rock TBM tunnels is standard practice, also for SRF estimation in drill-and-blast tunnels in massive rock. Recent work by fracture mechanics expert Baotang Shen shows that extension strain caused by Poisson’s ratio and the anisotropic stress near the tunnel wall actually causes (extensional) tensile fracturing, nothing to do with ‘compressive’ failure. Unstable propagation in shear might follow.

References

Barton N (1995) The influence of joint properties in modelling jointed rock masses. Keynote Lecture, 8th ISRM Congress, Tokyo, 3: 1023-1032, Balkema, Rotterdam

Barton N (2000) TBM Tunnelling in Jointed and Faulted Rock. 173p. Balkema, Rotterdam

Barton N (2007) Near-surface gradients of rock quality, deformation modulus, Vp and Qp to 1km depth. First Break, EAGE, 25, 53-60

Barton N, Gammelsæter B (2010) Application of the Q-system and QTBM prognosis to predict TBM tunnelling potential for the planned Oslo-Ski rail tunnels. Nordic Rock Mechanics Conf., Kongsberg, Norway

Barton N (2012) Reducing risk in long deep tunnels by using TBM and drill-and-blast methods in the same project – the hybrid solution. Keynote lecture. Risk in Underground Construction. J. Rock Mech. and Geotech. Eng., 4(2): 115-126

Barton N (2013) TBM prognoses for open-gripper and double-shield machines, challenges and solutions for weakness zones and water. Fjellsprengningskonferansen, Oslo, 21.1-21.17, Nov. 2013

Barton N and Shen B (2017) Risk of shear failure and extensional failure around over-stressed excavations in brittle rock. J. of Rock Mech. & Geotech. Eng., 9 (2): 210-225

Fawcett DF (1993) The effects of rock properties on the economics of full face TBMs. Comprehensive rock engineering. Hudson et al. Ch. 10. 4: 293-311. UK: Pergamon

Grimstad E, Barton N (1993) Updating of Q system for NMT. Proceedings of the International Symposium on Sprayed Concrete, Fagernes, 46-66

Hoek E, Brown E (1980) Underground excavations in rock. Institution of Mining and Metallurgy, 527p

Macias J, Barton N (2022) The NTNU and QTBM methods of prognosis with emphasis on hard-rock mixed-face problems. Fjellsprengningskonferansen, Oslo, 35.1-35.31

Martin CD, Kaiser PK, McCreath DR (1999) Hoek–Brown parameters for predicting the depth of brittle failure around tunnels. Can. Geotech. J., 36:136-151. https://doi.org/10.1139/t98-072

Shen CP, Tsai HC, Hsieh YS, Chu B (1999) The methodology through adverse geology ahead of Pinglin large TBM. Proc. RETC. Orlando, FL. Hilton & Samuelson (eds). Ch.8: pp. 117-137.Littleton, CO: Soc. for Mining, Metallurgy, and Exploration, Inc.

Shen B, Barton N (2018) Rock fracturing mechanisms around underground excavations. Journal of Geomechanics and Engineering, Korea Science. Vol. 16, No. 1 (2018) 35-47 DOI: https://doi.org/10.12989/gae.2018.16.1.035

Sundaram NM, Rafek AG (1998) The influence of rock mass properties in the assessment of TBM performance. Proc. 8th IAEG congress, Vancouver. Moore & Hungr (eds). 3553-3559. Rotterdam: Balkema